## Start Here
PROJECT INFORMATION
Project Name:
Organisers:
Phone numbers: | (more than one please)
Email:
Brief description of your project:
SAFETY PLAN CHECKLIST
1: Get your crew together to talk about your safety plan. It will take at least of couple of hours so make it an event!
2: Identify significant hazards associated with your project. Read the Help tab for definitions and explainations.
3: Identify the risks associated with each hazard. Brainstorming is the best way.
4: Identify the consequences and chances of something happening. Use the Risk Matrix to help you choose.
5: Identify the controls you will put in place to lessen each risk. Ideas and suggestions on the Help tab.
6: Lastly make an emergency plan to deal with any problems. Super important!
7: Send your completed plan to Kiwiburn before INSERT CUTOFF DATE

## Help
HELP, IDEAS, DEFINITIONS AND RESOURCES FOR COMPLETING YOUR SAFETY PLAN
Each section on this page has a corresponding section on the H&S Plan. The aim is to demonstrate that you have done everything reasonably practicable to identify hazards and manage risks. There are some common examples of how Hazards, Risks and Controls all fit together in the blue section.
HAZARDS - Hazards are things associated with your project that are or could be dangerous.
Fire is an obvious hazard especially at Kiwiburn as is electricity or sound. Someone completing nutting off is also a hazard but not such an obvious one. Hazards are usually connected to people, equipment or the environment.
PEOPLE - talk about all the different people who may be a part of or visit your project
Who do you expect to be at your activity?
Number of participants or volunteers? How will you cope with greater numbers? Do you have a limit?
What are their physical capabilities as volunteers or participants? Fitness, strength, size, shape, allergies, abilities …..
What are their mental capabilities as volunteers or participants? Feelings, anxieties, motivation, reliability, fatigue, cogniscance, sensibilities …..
Are there any cultural, social or psychological factors to consider?
Do they have any special skills or qualifications that could be useful? Building, electrical, psychology, first aid, hazardous substances, project management, health and safety …..
EQUIPMENT - talk about all the different equipment you will need for your project.
How will you give information to volunteers and participants? Signs, briefs, handouts, digital media .….
What kind of materials are you using?
What kind of tools are you using? How do you know your tools are safe?
How do you know you have the right kind of equipment for the job?
How do you know you have enough equipment? What will happen if you don't?
Is there any special equipment you may need? Rope, cameras, compass, fire extinguisher, first aid kit, life jackets, footwear .….
How are you moving your equipment?
Where are you storing your equipment?
Super important! If you are bringing a sound system, we need to know the system size as we are subject to some restrictions. If your sound system has not been approved by the paddock architects then you will not be allowed to use it and everyone would be super bummed. Please add sound as a hazard on to your H&S plan.
ENVIRONMENT - talk about all the different environmental factors, natural and man made.
How will the weather affect your activity? Sun, rain, wind, heat, cold, lightning.....
How will the time of day affect your activity? Daytime, nighttime, dinnertime …..
How will the terrain affect your activity? Hard, soft, wet, dry, where, what, familiar, unfamiliar…..
What natural hazards might there be? Bush, mountain, sea, river, beach, cliff …..
Are there any animal or insect hazards? Bees, boars, rabbits, piranhas, livestock …..
How accessible is help if you need it? Phone reception/credit, doctor, ranger, roads, tracks …..
Do you have a communication plan? How will you contact each other, Kiwiburn crew, security, emergency services ……
How will traffic or road use affect your activity? Don’t forget foot traffic.
How will other theme camps, art installations or activities affect your activity?
RISKS - Each hazard will have at least one risk associated with it.
Risks can be to people (health and safety), the environment, financial, legal or in rare cases cause a delay. Using power tools poses risks to both health and safety through injury and to the environment through damage or fire.
HEALTH AND SAFETY RISKS - talk about all the ways people may be affected by hazards
Death, serious injury, disability including irreversible health damage ….. :(
Hospitalisation for breakages, impact damage, disability, mental distress, foreign bodies …..
Medical treatment for sprains, impact damage, sunburn, dehydration, allergies …..
Superficial injury …..
Slight pain or discomfort …..
ENVIRONMENTAL RISKS - talk about all the possible effects on the enviroment
Severe permanent or irreversible damage or contamination ….. :(
Very serious environmental harm that will need years for recovery
Significant environmental harm that will need weeks for recovery
Minor transient environmental harm that will need days for recovery
Minor localised contamination but no environmental harm
FINANCIAL RISKS - talk about any financial risks to Kiwiburn organisers or yourselves that could be a result of your activities.
Categories range from insignificant <$1000 to catastrophic >$100,000
It is not anticipated any activities will pose financial risk unless there is significant law breaking resulting in a major incident or accident.
LEGAL RISKS - think about any legal risks your activities may pose
Risks can be to volunteers, participants or Kiwiburn organisers should sufficient breaches be found.
DELAYS - As Kiwiburn is a stand alone event it is not anticipated there will be any risks by theme camps or art installations that will pose a delay to the event proceeding. However if you can think of something you need to include it.
CONSEQUENCES are the result of a risk occuring.
Consequences can range from insignificant to castastrophic. Detailed information about the definition of consequences can be found on the Risk Matrix sheet.
CHANCES are the likelihood of a risk occuring.
These range from almost certain to rare. See the Risk Matrix for more information.
RISK FACTORS are based on consquences and chances
Once you have figured out the consequences of something happening and the chances of something happening a risk factor is applied.
Work out your risk factors by using the Risk Matrix. Risk factors range from very high to rare.
CONTROLS are what you apply to manage each risk.
You must always eliminate the risk where you are reasonably able to, otherwise you apply controls to reduce the consequences, the chances and ultimately the risk factor associated with each risk. Keeping everyone safe is the aim of the game.
Each theme camp or art installation will have its own set of hazards and risks, here are a few to get you started.
SUGGESTED CONTROLS FOR SOME COMMON HAZARDS AND RISKS
Hazard = Driving on site / moving vehicles
Health and Safety Risks = People being hit by vehicles, collisions between vehicles, collisions between vehicles and naturals structures e.g trees or manmade structures e.g.tents, unstable loads, falling from vehicles …..
Controls = Isolate vehicles from people, ensure vehicles and drivers are fit for purpose, use spotters or directors, collaborate with other activities, observe limits, use signs …..
Hazard = Hazardous Substances e.g. petrol for generators or gas for cooking
Health and Safety Risks = Injury, burns, poisoning, respiratory problems or dermatitis due to exposure …..
Health and Safety Controls = All hazardous substances must be clearly identified, fit for purpose storage containers and defined storage areas including good ventilation, competant personnel in storage, handling and refuelling …..
Environmental Risks = Petrol and gas are highly flammable and pose a high risk of fire and/or explosion if there is a source of ignition nearby, leakage, spilling during refuelling …..
Environmental Controls = All hazardous substances must be clearly identified, fit for purpose storage containers and defined storage areas including good ventilation and shelter from heat sources such as the sun, competant personnel in storage, handling and refuelling, no naked lights or smoking within 20m of flammable liquids .....
Hazard = Food Preparation and Service
Health and Safety Risks = Contamination or poisoning by incorrectly stored food or poor personal hygiene, cuts and burns within the preparation area, slips, trips and falls within the preparation area, cuts and infection due to rubbish handling …..
Health and Safety Controls = Good food handling practices including storage and monitoring, hygienic practices such as surface cleaning and hand washing facilities, competant personnel, equipment safe and fit and for purpose, safe and clutter free walkways and work areas, clearance around hot plates, cooktops or barbeques, rubbish bins ....
Environmental Risks = Rubbish, fire …..
Environmental Controls = Rubbish storage and disposal plan, cooking equipment fit for purpose, risks identified with hazardous substance handling and storage, fire extinguishers onsite …..
Hazard = Intoxicated / drug affected people
Kiwiburn does not condone excessive consumption of alcohol nor the use of illegal substances and reminds all theme camps and art installations of New Zealand Law in this regard. Kiwiburn recommends that theme camps and art installations practice host responsibility at all times. Look out for each other.
Health and Safety Risks = physical injury to self or others due to impaired judgement or control, mental injury to self due to psychotic episode
Health and Safety Controls = Host responsibility at the activity including competant personnel who can recognise the signs and symptoms when someone is in trouble, first aid facilities and safe spaces, host responsibility also means not letting people wander off alone if they are in need of assistance, having a communication plan and strategy to get help .....
Environmental Risks = Damage to natural environment, theme camp or art installation by intoxicated or drug affected person
Environmental Controls = Host responsibility at the activity including competant personnel and having a communication plan and strategy to get help …..
Hazard = Sound
Health and Safety Risks = Hearing loss or damage due to sound systems or use of tools
Health and Safety Controls = Sound system levels monitored and kept within Kiwiburn guidelines, participants dissuaded from risky behaviours such as putting ears to speakers or spending extended periods directly in line of sound, use of PPE (earmuffs) when using power tools .....
Financial and Legal Risks = Excessive sound levels breaching restrictions possibly resulting in fines and/or bans on future events
Financial and Legal Controls = Sound system levels monitored and kept within Kiwiburn guidelines
REASSESSING THE RISK FACTORS
Once you have figured out all your risks and the controls needed to manage them, you reassess the consequences, chances and risk factors using exactly the same principles.
Something to remember is you can't always reduce the consequence - getting hit by a car is always going to hurt but you can reduce the chance of it happening.
The risk factor should always come down or you have done something wrong in your planning.
Activities that are judged too risky by Kiwiburn (or the law) will not be allowed to proceed.
RESOURCES - talk about all the things you need to gather to make it happen
Resources can be people like absailing instructors, chefs, architects, electricians or just extra hands
Resources can also be information like guidelines or instructions
Resources can also be equipment like fire extinguishers, rubbish bins, sunscreen, walkie talkies
Resources can also be plans like communication plans or traffic management
ASSIGN RESPONSIBILTIES - talk about who is responsible for each resource
Organising something like a theme camp is a lot of work and besides it's more fun to share and collaborate. Talk about each other's capabilities and any qualifications like unit standards that could be useful
Agree on time frames and check things off as they have been done
EMERGENCY PLAN - this is the last section :)
It's all very well and good having identified your hazards and risks but what will you do if something goes Pete Tong? Having a good emergency plan for each risk is the last part of your H&S Plan.
Make a step by step response for each risk. They don’t have to be long winded or complicated just effective. Emergency plans can include the use of controls such as safety equipment.
Include that you understand your reporting responsibilities for any incidents or accidents to Kiwiburn.
EXAMPLE - Medical emergencies
1. Ensure your crew know who your first aid people are and where the first aid kit is kept
2. Have a competant person assess and possibly treat the injury
3. Have a communication plan if outside help is needed
4. Report the incident or accident to Kiwiburn
EXAMPLE - Fire in the kitchen
1. Have competent fire wardens
2. Ensure your crew know where the fire equipment is kept and how to use it (only if it is safe to do so)
3. Have an evacuation plan to get everyone out
4. Have an assembly area away from the fire
5. Have a communication plan if outside help is needed
6. Report the incident or accident to Kiwiburn
EXAMPLE - High winds damaging your installation
1. Have a competent person check anchor points on all your structures
2. Have additional ropes and stakes if needed
3. Have a plan to ressess them if required
4. Have a plan to adapt the activity or structure as required
5. Report any incident or accident to Kiwiburn
RESOURCES FOR YOU TO COMPLETE YOUR PLAN
http://www.kiwiburn.com/participate/theme-camps/
http://www.kiwiburn.com/participate/theme-camps/theme-camp-setup-guide/
http://www.kiwiburn.com/participate/art/
http://www.worksafe.govt.nz/worksafe/hswa/health-safety
http://www.worksafe.govt.nz/worksafe/hswa/health-safety/how-to-manage-work-risks
Email themecamps@kiwiburn.com for help
Note on B51: sam: KB - can you please get your legal beagles to check this section and amend as necessary? And the bit in the blue section below about sound

## H&S Plan
PROJECT NAME
These are free text columns. Use as much detail as possible. Don't forget to include sound if you are bringing a sound system. Refer to the Help sheet for more information. |  | These are drop down columns. Look for the little arrow to the right of each cell and use the definitions on the Risk Matrix to help you choose. |  |  |  | Enter all the things you can do to lessen each risk. Refer to the Help sheet for more information. | Rechoose the drop downs based on the controls you will put in place. Use the Risk Matrix again to help. |  |  | Enter what needs to happen for the controls to work. | Enter the name of the person responsible. | Enter any relevant Unit Standards qualifications | For your own records |  | Enter what will happen in the event of an emergency | Enter the name of the person responsible | Enter any relevant Unit Standards qualifications | Anything else you can think of goes here
HAZARD NAME | RISKS ASSOCIATED WITH THE HAZARD | TYPE OF RISK | CONSEQUENCES OF SOMETHING HAPPENING | CHANCES OF SOMETHING HAPPENING | RISK FACTOR | CONTROLS TO LESSEN THE RISK | REVISED CONSEQUENCES OF SOMETHING HAPPENING | REVISED CHANCES OF SOMETHING HAPPENING | REVISED RISK FACTOR | RESOURCES TO GATHER, JOBS TO BE DONE, THINGS TO ORGANISE | ASSIGNED TO | FIRST AID, WORKING AT HEIGHTS, HAZARDOUS SUBSTANCES ETC | STATUS | DATE SORTED | STEP BY STEP EMERGENCY PLAN FOR EACH RISK | RESPONSIBLE ADULT | FIRST AID, WORKING AT HEIGHTS, HAZARDOUS SUBSTANCES ETC | EXTRA FOR EXPERTS

## Risk Matrix
RISK MATRIX
CONSEQUENCE | Almost Certain | Likely | Possible | Unlikely |  | Rare
CATASTROPHIC | Very High | Very High | Very High | Very High |  | Very High
| -25 | -24 | -22 | -20 |  | -19
MAJOR | Very High | Very High | Very High | High |  | High
| -23 | -21 | -18 | -14 |  | -12
MODERATE | High | High | High | Medium |  | Medium
| -17 | -16 | -13 | -9 |  | -6
MINOR | High | High | Medium | Low |  | Low
| -15 | -11 | -8 | -5 |  | -3
INSIGNIFICANT | Medium | Medium | Low | Low |  | Low
| -10 | -7 | -4 | -2 |  | -1
RISK CONSEQUENCE
DESCRIPTOR | Health and Safety | Environmental | Financial | Legal |  | Delay
CATASTROPHIC | Death or serious injury / illness to one or more people causing permanent disability, including irreversible health damage | Severe IRREVERSIBLE environmental harm or contamination with PERMANENT damage | Greater than $100,000 | Significant prosecution and fines. Serious litigation. Class actions |  | Indefinite delay or stoppage
MAJOR | Injury / illness causing permanent partial or temporary severe disability including serious health damage and/or needing hospitalisation | Very serious long term environmental harm or contamination that needs YEARS for recovery | Between $50,000 and $100,000 | Major breach of regulation and major litigation |  | Greater than 3 months
MODERATE | Injury / illness causing temporary disability including reversible health effects. May need medical treatment and/or alternative work duties or may result in one or more days lost | Significant environmental harm or contamination that needs WEEKS for recovery | Between $25,000 and $50,000 | Serious breach of regulations with investigation and report to authorities, fine possible |  | Between 3 weeks and 3 months
MINOR | Superficial injury / illness that may need First Aid and/or medical assessment | Minor transient environmental harm or contamination that needs DAYS for recovery | Between $1,000 and $25,000 | Minor legal issues and non-compliance |  | Between 1 week and 3 weeks
INSIGNIFICANT | Slight pain and/or discomfort | Minor localised contamination but NO environmental harm | Less than $1,000 | Minor breaches of regulations |  | No impact or less than 1 week
RISK LIKELIHOOD
LIKELIHOOD | Description |  |  |  | Probability (Frequency)
ALMOST CERTAIN | The event is expected to occur in most circumstances |  |  |  | 75%
LIKELY | The event will probably occur in most circumstances |  |  |  | 50%
POSSIBLE | The event should occur at some time |  |  |  | 25%
UNLIKELY | The event could occur in most circumstances |  |  |  | 10%
RARE | The event may occur only in exceptional circumstances |  |  |  | 1%
Password protected paddock2016

## Locked Sheet (hidden)
Drop down type | Drop down consequences | Drop down chances | Drop down risk
Health and Safety | Catastrophic | Almost Certain | Very High
Enviromental | Major | Likely | High
Financial | Moderate | Possible | Medium
Legal | Minor | Unlikely | Low
Delay | Insignificant | Rare